## Menu
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
MALARIA 1, New Funding Model | Grant No.: GHA-M-AGAMAL
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
Indicators
Financial information
Name: | Definition |  | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. |  | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by category | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective. |  | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. |  | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period.
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. |  | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement.
Management Information
Name | Definition |  | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. |  | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. |  | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. |  | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time, this reporting period | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. |  | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). |  | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. |  | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, Approved on 28 August, 2012) |  | Measurement | Data Source
Pr1. Percentage of population in targeted districts sprayed by indoor residual spraying in the last 12 months | The numerator for this indicator is obtained by counting the number of usual household residents in houses adequately sprayed. Adequacy is determined by the uniformity of spraying in the household, spraying in all rooms in the house and spraying at intervals consistent with the manufacturer’s recommendation in the target area. Denominator information is the projections from 2010 Population census information. |  | PS= # of individual living in houses that were sprayed with a residual insecticide during an IRS campaign in the last 12 months PM= #Population at risk for malaria Population Coverage =PS/PM*100 | Daily spray cards, as summarized in the program data base. Spray operator is the original source of information.
Pr2. No. and percentage of structures in targeted districts sprayed by indoor residual spraying in the last 12 months | Number and percentage of structures (rooms/dwellings) in targeted districts sprayed by indoor residual spraying. These are structures (rooms/dwellings) sprayed in the course of the spray season. |  | F= # sprayable structures Targeted S= # sprayable structures sprayed IRS Coverage (c) = S/F* 100 | Daily spray cards, as summarized in the program data base Spray operator is the original source of information.
Indicator Number: Name (Perf Framework No.) | Definition |  | Measurement | Data Source
The indicators should be selected from the Performance Framework by the PRs and members of the CCM or the CCM Technical Committee. |  |  |  | Performance Framework
Menu

## Data Entry
|  |  |  | Data Entry | 2016-02-12
Grant information
| Country: | Ghana |  | Title of the Grant: |  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying
| Grant No.: | GHA-M-AGAMAL |  | Component: |  | MALARIA | Funding: | 13325139.3036
| Principal Recipient: | AngloGold Asanti (Ghana) Malaria Ltd |  |  | Round: | 1 | Phase: | New Funding Model
| Start Date (dd/Mmm/yy): | 2015-03-01 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A2 |  | Fund Portfolio Manager: |  | Mark Saalfeld
Information reporting period
| Report Period: | P4 | From: | 2015-10-01 | To: | 2015-12-31 | Date of entry of information: |  | 2016-02-12
| Prepared by: |  | AGAMAL LTD
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | $
F1: Budget and disbursements by Global Fund
|  | Jan-Mar 2015 | Apr - Jun 2015 | Jul - Sept 2015 | Oct - Dec 2015 | Jan - Mar 2016 | Apr - Jun 2016 | Jul - Sept 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 | Jul - Sept 2017 | Oct - Dec 2017
3728250.7483
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 5632849.5932
| Budget (in $) | P1: 3728250.7483; P2: 1904598.8449; P3: 565239.3654; P4: 521840.4334 | 166.3% |  |  | 6198088.9586
| Disbursements by GF (in $) | P1: 4454139; P2: 6719929; P3: 0; P4: 0 |  |  |  | 6719929.392
| Cumulative budget | 3728250.7483 | 5632849.5932 | 6198088.9586 | 6719929.392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements | 4454139 | 11174068 | 11174068 | 11174068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 0% | 0% | 0% | 166.3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by category
| Category | P1: Cumulative Budget (in $); P2: Cumulative Expenditures (in $); P3: % of budget; P4: Q4 burn rate; P5: Q3 burn rate
| Human Resources | P1: 3077785.824; P2: 2785565.6; P3: 45.8%; P4: 90.51%; P5: 83.57%
| Travel related costs | P1: 529020.9803; P2: 233429.57; P3: 7.872%; P4: 44.12%; P5: 36.71%
| External Professional services | P1: 1042598.397; P2: 345714.11; P3: 15.52%; P4: 33.16%; P5: 30.16%
| Health Products - Non Pharmaceuticals | P1: 0; P2: 5088011.34; P3: 0%; P4: #DIV/0!; P5: #DIV/0!
| Health Products - Equipment | P1: 133278.59; P2: 60044.77; P3: 1.983%; P4: 45.05%; P5: 32.25%
| Procurement and Supply-Chain Management costs | P1: 27300; P2: 221279.63; P3: 0.4063%; P4: 810.5%; P5: 791.6%; P6: Clearance cost for insecticide 5m that was not budgeted for (was budgeted in 2014)
| Infrastructure | P1: 12000; P2: 9983.59; P3: 0.1786%; P4: 83.2%; P5: 42.91%
| Non-health equipment | P1: 1566471.9311; P2: 410214.44; P3: 23.31%; P4: 26.19%; P5: 19.58%
| Communication Material and Publications | P1: 164303.4829; P2: 7253.65; P3: 2.445%; P4: 4.415%; P5: 8.262%
| Programme Administration costs | P1: 167170.1868; P2: 173563.43; P3: 2.488%; P4: 103.8%; P5: 67.19%
| Commitment: 850,604 USD (50% for insecticides + 285,000 for parasite prevalence study) | P3: 79.65%
| Total | P1: 6719929.392; P2: 9335060.13; P3: 138.9%; P4: OK: Data match
138.9%
| F3: Disbursements and expenditures | P2: 63.2% |  |  |  | 0
| P4: | P1: 521840.392; P2: 757624.13; P3: 145.2% |  |  |  | 0
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Totals (in $); P5: Notes/Calc |  |  | 0
| Disbursed by Global Fund | P1: 6719929; P2: 0; P3: 6719929
| PR expenditure | P1: 8577435.67; P2: 757624.46; P3: 9335060.13
| Disbursed to SRs | P1: 0; P2: 0; P3: 0
| SR expenditures | P1: 0; P2: 0; P3: 0
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 45; P3: Days from end of previous reporting period until accepted PU/DR was sent to LFA
| Days taken for disbursement to reach PR | P1: 45; P2: -; P3: Days from receipt of accepted PU/DR by LFA
| Days taken for disbursement to reach SRs | P3: Average days from receipt by PR to receipt by SRs
| Management Information: | P6: Enter management data in every blue cell.
| M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | P3: as of; P4: 2015-12-31
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
Conditions Precedent (CPs) | bar: P2 to P4
Time Bound Actions (TBAs) | bar: P2 to P4
| M2: Status of key PR management positions | P2: as of; P3: 2015-12-31
|  | Planned | Filled | Vacant |  |  |  | notes
| PR | P7: notes
| M3: Contractual arrangements (SRs) | P4: as of; P5: 2015-12-31
|  | Identified | Assessed | Approved | Signed | Receiving Funding |  | Check for any changes in SR status
| SRs | P1: 0; P2: 0; P3: 0; P4: 0; P5: 0; P7: notes
| M4: Number of complete reports received on time, this reporting period | P3: which ends; P4: 2015-12-31
|  | # Expected | # Received | Pending
| SSR to SR | P1: 0; P2: 0; P3: 0; P7: notes
| SRs to PR | P1: 0; P2: 0; P3: 0; P5: OK: SR data match.; P7: notes
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | Jan-Mar 2015 | Apr - Jun 2015 | Jul - Sept 2015 | Oct - Dec 2015 | Jan - Mar 2016 | Apr - Jun 2016 | Jul - Sept 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 | Jul - Sept 2017 | Oct - Dec 2017
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 56761.7683; P2: 19574.375; P3: 37368.0717; P4: 19574.375
| Obligations | P1: 5088011.34; P2: -5088011; P3: 0; P4: 481080.2 | Obligations
| Expenditures | P1: 29446.19; P2: 5091030.35; P3: 4209.72; P4: 23370.93 | Expenditures
| Cumulative Budget Approved* | 56761.7683 | 76336.1433 | 113704.215 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | 133278.59 | Budget Approved*
| Obligations | 5088011.34 | 0.34 | 0.34 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | 481080.54 | Obligations cumulative
| Expenditures cumulative | 29446.19 | 5120476.54 | 5124686.26 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | 5148057.19 | Expenditures cumulative
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
| M6: Difference between current and safety stock | P5: as of; P6: 2015-12-31
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2) = (1) x 30 Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4) = (2) x (3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6) = (5) / (4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8) = (6) - (7) Difference between current stock and safety stock
| MALARIA | P1: AS/MQ; P2: 0; P3: 0; P4: 0; P6: 0; P8: 0
|  | Al/Lum | 0 | 0 | 0 |  | 0 |  | 0
| Programmatic Information: | P9: Enter performance data in every yellow cell.
|  | P6: Jan-Mar 2015; P7: Apr - Jun 2015; P8: Jul - Sept 2015; P9: Oct - Dec 2015; P10: Jan - Mar 2016; P11: Apr - Jun 2016; P12: Jul - Sept 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 | Jul - Sept 2017 | Oct - Dec 2017
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Percentage of population in targeted areas sprayed with IRS in the last 12 months |  |  | 1.1 | YES | Target | P2: 871071; P3: 0; P4: 0 | Target
[6 empty] | Achieved | P2: 771553; P3: 0; P4: 0 | Achieved
| Number of structures sprayed in targeted areas with IRS in the last 12 months |  |  | 1.2 | YES | Target | P2: 809876; P3: 0; P4: 0 | Target
[6 empty] | Achieved | P2: 788516; P3: 0; P4: 0 | Achieved
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Percentage of population in targeted areas sprayed with IRS in the last 12 months |  |  | 1.1 | YES | Target | 0 | 871071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 771553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Number of structures sprayed in targeted areas with IRS in the last 12 months |  |  | 1.2 | YES | Target | 0 | 809876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 788516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Menu
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B76: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B77: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B83: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B98: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.

## Grant Detail
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
Country: | Ghana |  | Title of the Grant: |  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying
Component: | MALARIA | Grant No. | GHA-M-AGAMAL | Start Date: |  | 2015-03-01 | Funding: | 13325139.3036
Round: | 1 | Phase: | New Funding Model | Principal Recipient: |  | AngloGold Asanti (Ghana) Malaria Ltd
Report Period: | P4 | from: | 2015-10-01 | to: |  | 2015-12-31 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Mark Saalfeld
Prepared by: | AGAMAL LTD |  |  | Report preparation date: |  | 2016-02-12
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
1 | New Funding Model |  |  |  | Report Period: |  | P4
Latest Rating: | A2 |  | AngloGold Asanti (Ghana) Malaria Ltd |  | From: |  | 2015-10-01
|  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying |  |  |  | To: | 2015-12-31
Financial Indicators
F1: Budget and disbursements by Global Fund - ($) Report Period: P4 |  |  |  | F3: Disbursements and expenditures - ($) Report Period: P4
Comments: | AGAMAL's budget for t he period under review was $521,840 and had received its total annual disbursement in prior period. AGAMAL therefore did not receive any funds in the period under review. |  |  | Comments: | AGAMAL received its annual budget disbursement in prior period and therefore did not receive any funding during the period under review. However, AGAMAL's total expenditure for the period October to December,2015 was $757,624.46.The excess expenditure over disbursement received was as a result of timing differences between budget and actual payment.
F2: Budget and actual expenditures by category - ($) Report Period: P4 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P4
Comments: | Generally, there is a positive variance in all the cost categories except Health Products, Procurement and Supply Chain Management & Programme Administration.The positive variance is as a result of the timing of the start of the NFM. The budget was made to cover 12 months however NFM implementation covered 10 months ie March to December 2015. The negative variance on Health Products & Equipment is as a result of insecticides procured and paid for which includes quantities meant to be used for 2016 operations rolled over from the old grant. Port clearing and handling charges on the insecticides were not budgeted for in the period under review which resulted in the negative variance on the Procurement and Supply Chain Management cost category. Finally, rent for Wa Zonal/District office was paid in advance in December 2015 instead of January 2016 as provided for in the budget. Hence the negative variance on the Programme Administration cost category. |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR |  | 45 | -
|  |  |  | Days taken for disbursement to reach SRs |  | 0 | 0
Menu

## Programmatic
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
1 | New Funding Model | [7 empty] | Report Period: |  | P4
Latest Rating: | A2 |  | AngloGold Asanti (Ghana) Malaria Ltd | [6 empty] | From: | 2015-10-01
|  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying | [7 empty] | To: | 2015-12-31 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Percentage of population in targeted areas sprayed with IRS in the last 12 months |  |  |  | Number of structures sprayed in targeted areas with IRS in the last 12 months |  |  |  | 0
Comment: | No population coverage for the period under review as there was no spraying done between October to December, 2015. AGAMaL is currently spraying with a long lasting insecticide (Actelic 300CS) with residual efficacy of about 9 months. Thus only one round of spraying would be done each spray year. |  |  | Comment: | The last spraying for the year was done from April to June, 2015 and data already reported to CCM. Spraying was not done for the current reporting period under review; hence the entries for Target and Achieved are zero |  |  | Comment:
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | ≥ 90% | Comments |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Percentage of population in targeted areas sprayed with IRS in the last 12 months |  |  | 0 | 0 | 0% |  |  | No population coverage for the period under review as there was no spraying done between October to December, 2015. AGAMaL is currently spraying with a long lasting insecticide (Actelic 300CS) with residual efficacy of about 9 months. Thus only one round of spraying would be done each spray year. |  |  |  |  | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of structures sprayed in targeted areas with IRS in the last 12 months |  |  | 0 | 0 | 0% |  |  | The last spraying for the year was done from April to June, 2015 and data already reported to CCM. Spraying was not done for the current reporting period under review; hence the entries for Target and Achieved are zero |  |  |  |  | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  |  | 0 | 0 | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[5 empty] | 0% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[13 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Management
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
1 | New Funding Model |  |  |  |  | Report Period: |  | P4
Latest Rating: | A2 |  | AngloGold Asanti (Ghana) Malaria Ltd |  |  | From: |  | 2015-10-01
|  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying |  |  |  |  | To: | 2015-12-31
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P4 |  |  |  | M2: Status of key PR management positions Report Period: P4
Comments: |  |  |  | Comments:
l8
M3: Contractual arrangements (SRs) Report Period: P4 |  |  |  | M4: Number of complete reports received on time, this reporting period Report Period: P4
Comments: |  |  |  | Comments:
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P4
Comments: | Out of a budget of $133,279 $5,148,057 was spent on health products and equipment. The deficit is as a result of a roll over cost prior to the New Funding Model. Its associated budget in 2014 was not fully utilised because of delays in procuring them due to Global Fund's request for Quality Assurance Testing and the general change in spray plan. |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | MALARIA | AS/MQ |  | 0
[5 empty] | Al/Lum |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Actions
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
| 1 | New Funding Model |  |  |  | Report Period: |  | P4
| Latest Rating: | A2 |  | AngloGold Asanti (Ghana) Malaria Ltd |  | From: |  | 2015-10-01
|  |  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying |  |  |  | To: | 2015-12-31
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the status of actions on previous decisions?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Notes
Malaria | 1 |  | Notes that don't fit into dashboard cells. This list can be updated each period.
MoH |  |  |  |  | Notes
Comment Date | Rptg Period | Author | PR or CCM | Indic # | Comment
March 30, 2013 | P7 | Frank Amoyaw | PR | 1.1 | At the end of week 7 - March 30, the expected number of structures to be sprayed was 491,772 against a cumulative sprayed structures of 172,355 - representing 12.27 of the end of season target (Jan-June, 2013). Refer to Attached Performance tracker. Please note that PR reports per semester basis, and this representation is intended to offer CCM management information on current performance as at the end of P7
March 30, 2013 | P7 | Frank Amoyaw | PR | 1.5 | A total of 376 spray operators, 52 team leaders were engaged. Cumulative figure thus becomes 1137
September 10, 2013 | P10 | Frank Amoyaw | PR | 1.1 | The minimum number of structures targeted for the period was 1,194,305 (85%) out of a total of 1,405,065 structures as stated in the PF for the period: The inability to reach the minimum set target for the period resulted from significant delays in the insecticide clearing process at the port leading to stock-outs and hence lost operational time. This tremendously affected the weekly expected spray coverage and the consequent reduction in total coverage for the period.
September 10, 2013 | P10 | Frank Amoyaw | PR | 1.5 | Some districts did not have the full complement of spray operators due to issues with medical surveillance results and some isolated cases of vacation of post. This led to the shortfall in the total number of persons trained.
September 10, 2013 | P10 | Frank Amoyaw | PR | 1.6 | Although there were no stockouts prior to the start of spraying, we encountered stockouts in the course of the spraying season.
2016-03-06 | P3 | Ignatius Williams | PR |  | As per the 2015-2016 period, only one indicator i.e. the population covered in targetd areas is required. However the CCM has requested that the dashboard be populated with the number of structures sprayed for the purpose of this reporting period. Again, the last spraying for the year was done from April to June, 2015 and data already reported to CCM.

## Recommendations
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
1 | New Funding Model |  |  |  |  | Report Period: | P4
Latest Rating: | A2 |  | AngloGold Asanti (Ghana) Malaria Ltd |  |  | From: | 2015-10-01
|  |  | Accelerating Access -- Home-Based Care & Indoor Residual Spraying |  |  | To: | 2015-12-31
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | AGAMAL's budget for t he period under review was $521,840 and had received its total annual disbursement in prior period. AGAMAL therefore did not receive any funds in the period under review.
F2 |  | Generally, there is a positive variance in all the cost categories except Health Products, Procurement and Supply Chain Management & Programme Administration.The positive variance is as a result of the timing of the start of the NFM. The budget was made to cover 12 months however NFM implementation covered 10 months ie March to December 2015. The negative variance on Health Products & Equipment is as a result of insecticides procured and paid for which includes quantities meant to be used for 2016 operations rolled over from the old grant. Port clearing and handling charges on the insecticides were not budgeted for in the period under review which resulted in the negative variance on the Procurement and Supply Chain Management cost category. Finally, rent for Wa Zonal/District office was paid in advance in December 2015 instead of January 2016 as provided for in the budget. Hence the negative variance on the Programme Administration cost category.
F3 |  | AGAMAL received its annual budget disbursement in prior period and therefore did not receive any funding during the period under review. However, AGAMAL's total expenditure for the period October to December,2015 was $757,624.46.The excess expenditure over disbursement received was as a result of timing differences between budget and actual payment.
F4
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1
M2 |  |  | #DIV/0! | #DIV/0!
M3
M4
M5 |  | Out of a budget of $133,279 $5,148,057 was spent on health products and equipment. The deficit is as a result of a roll over cost prior to the New Funding Model. Its associated budget in 2014 was not fully utilised because of delays in procuring them due to Global Fund's request for Quality Assurance Testing and the general change in spray plan.
M6
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
Pr1 - trend |  | No population coverage for the period under review as there was no spraying done between October to December, 2015. AGAMaL is currently spraying with a long lasting insecticide (Actelic 300CS) with residual efficacy of about 9 months. Thus only one round of spraying would be done each spray year.
Pr2 - trend |  | The last spraying for the year was done from April to June, 2015 and data already reported to CCM. Spraying was not done for the current reporting period under review; hence the entries for Target and Achieved are zero
Pr3 - trend
Pr1 |  | No population coverage for the period under review as there was no spraying done between October to December, 2015. AGAMaL is currently spraying with a long lasting insecticide (Actelic 300CS) with residual efficacy of about 9 months. Thus only one round of spraying would be done each spray year.
Pr2 |  | The last spraying for the year was done from April to June, 2015 and data already reported to CCM. Spraying was not done for the current reporting period under review; hence the entries for Target and Achieved are zero
Pr3
Pr4
Pr5
Pr6
Pr7
Pr8
Pr9
Pr10
Menu

## Setup (hidden)
Dashboard: Ghana - MALARIA (AngloGold Asanti (Ghana) Malaria Ltd)
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
[7 empty] | Condoms | Burundi
[7 empty] | HIV test kits | Cambodia
[7 empty] | HIV confirmation kits | Cameroon
This dashboard was customised from GF's January 2010 generic file, | [7 empty] | Cape Verde
<CCM Generic Dashboard_EN_fixed.xls> [received 26jan'10] | [7 empty] | Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe