## Menu
Dashboard: Ghana - HIV / AIDS
HIV / AIDS Round 9, NFM | Grant No.: GHA-H-GAC-786
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Ghana - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, June 2007) | Measurement | Data Source
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Ghana |  | Title of the Grant: |  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting
| Grant No.: | GHA-H-GAC-786 |  | Component: |  | HIV / AIDS | Total Funding: | 12905454
| Principal Recipient: | Ghana AIDS Commission |  |  | Round: | Round 9 | Phase: | NFM
| Start Date (dd/Mmm/yy): | 2015-07-01 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A1 |  | Fund Portfolio Manager: |  | Mark Saalfeld
Information reporting period
| Report Period: | Q1 | From: | 2015-07-01 | To: | 2015-09-30 | Date of entry of information: |  | 2015-11-15
| Prepared by: |  | GAC Core Team
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | $
F1: Budget and disbursements by Global Fund
|  | July - Sep 2015 | Oct -Dec 2015 | Jan-Mar 2016 | Apr-Jun 2016 | July - Sep 2016 | Oct -Dec 2016 | Jan-Mar 2017 | Apr-Jun 2017 | July - Sep 2017 | Oct -Dec 2017
Disbursement
| Reporting period | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | % Cumulative
| Budget (in $) | 1321451.38 | 1469906.7 | 1168329.84 | 1457407.65 | 1034175.49 | 1006489.59 | 1002545.51 | 1273185.81 | 1371210.73 | 1800751.02 | 100.8%
| Disbursements by GF (in $) | Q1: 1332486
| Cumulative budget | 1321451.38 | 2791358.08 | 3959687.92 | 5417095.57 | 6451271.06 | 7457760.65 | 8460306.16 | 9733491.97 | 11104702.7 | 12905453.72
| Cumulative disbursements | 1332486 | 1332486 | 1332486 | 1332486 | 1332486 | 1332486 | 1332486 | 1332486 | 1332486 | 1332486
|  | 100.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0% | 0% | 0%
F2: Budget and actual expenditures by Grant Objective
-11034.62
| Grant INTERVENTION | Q1: Cumulative Budget (in $); Q2: Cumulative Expenditures (in $); Q3: BY Module; Q4: Cumulative Budget (in $); Q5: Cumulative Expenditures (in $)
| BCC Outreach | Q1: 302154.78; Q2: 5993.61; Q3: MSM; Q4: 247576.3; Q5: 6145.5975
| HIV Testing and Counseling | Q1: 74183.42; Q2: 0; Q3: FSW; Q4: 633044.58; Q5: 40634.4895
| Care and Support (NHIS) | Q1: 49231.64; Q2: 32341.86; Q3: CSS; Q4: 225586.33; Q5: 32722.7575
| Distribution of Condom | Q1: 15576.17; Q2: 0; Q3: Program Mgt; Q4: 215244.17; Q5: 159322.1775
| Improve Coordination | Q1: 880305.37; Q2: 200489.552; Q3: TOTAL; Q4: 1321451.38; Q5: 238825.022
| Total | Q1: 1321451.38; Q2: 238825.022; Q4: OK: Data match
18.07%
F3: Disbursements and expenditures
|  | Prior to reporting period | Current reporting period | Total Spent and Disbursement (in $)
| Disbursed by Global Fund | Q2: 1332486; Q3: 1332486
| PR expenditure and disbursement | Q2: 242605.87; Q3: 242605.87
| Disbursed to SRs | Q2: 34667.45; Q3: 34667.45
| SR expenditures | Q2: 30886.602; Q3: 30886.602
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | Q1: 45; Q2: 44
| Days taken for disbursement to reach PR | Q1: 10; Q2: 10
| Days taken for disbursement to reach SRs | Q1: 3; Q2: 3
| Management Information: | Q6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) | Q5: 0
| Time Bound Actions (TBAs) | Q5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | Q3: 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | Q1: 2; Q2: 2; Q3: 2; Q4: 2; Q5: 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | Q1: 4; Q2: 0; Q3: 4
| SRs to PR | Q1: 2; Q2: 0; Q3: 2
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | Q1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | Q9: Enter performance data in every yellow cell.
|  | Q6: July - Sep 2015; Q7: Oct -Dec 2015; Q8: Jan-Mar 2016; Q9: Apr-Jun 2016; Q10: July - Sep 2016 | Oct -Dec 2016 | Jan-Mar 2017 | Apr-Jun 2017 | July - Sep 2017 | Oct -Dec 2017
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10
TOP 3 | Pr1. # male & female condoms distributed to FSW. |  |  | 1 | No | Target | Q1: 1500000; Q2: 3000000; Q3: 4500000; Q4: 6000000
[6 empty] | Achieved | Q1: 0
| Pr2. # male condoms distributed to MSMs. |  |  | 1 | No | Target | Q1: 100000; Q2: 200000; Q3: 300000; Q4: 400000
[6 empty] | Achieved | Q1: 0
| Pr3. # of FSW who received testing and counseling for HIV and received their test results |  |  | 2 | Yes | Target | Q1: 1500; Q2: 3000; Q3: 5077; Q4: 7155
[6 empty] | Achieved | Q1: 0
| Pr4. # of MSM who received testing and counseling for HIV and received their test results |  |  | 2 | Yes | Target | Q1: 375; Q2: 750; Q3: 1993; Q4: 3237
[6 empty] | Achieved | Q1: 0
| Pr5. # of FSW reached with HIV prevention programs (interventions) |  |  | 3 | Yes | Target | Q1: 1380; Q2: 2760; Q3: 6883; Q4: 11007
[6 empty] | Achieved | Q1: 0
| Pr6. # of MSM reached with HIV prevention programs (interventions) |  |  | 3 | Yes | Target | Q1: 575; Q2: 1150; Q3: 4621; Q4: 8092
[6 empty] | Achieved | Q1: 0
| Pr7. # of PLHIV registered in the National Health Insurance Scheme |  |  | 6 | Yes | Target | Q1: 500; Q2: 1000; Q3: 1500; Q4: 2000
[6 empty] | Achieved | Q1: 1134
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10
| Pr1. # male & female condoms distributed to FSW. |  |  | 1 | No | Target | 1500000 | 3000000 | 4500000 | 6000000 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | Q1: 0; Q8: 0; Q9: 0; Q10: 0
| Pr2. # male condoms distributed to MSMs. |  |  | 1 | No | Target | 100000 | 200000 | 300000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | Q1: 0; Q8: 0; Q9: 0; Q10: 0
| Pr3. # of FSW who received testing and counseling for HIV and received their test results |  |  | 2 | Yes | Target | 1500 | 3000 | 5077 | 7155 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | Q1: 0; Q8: 0; Q9: 0; Q10: 0
Note on B69: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B70: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B76: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B91: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Ghana - HIV / AIDS
Country: | Ghana |  | Title of the Grant: |  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting
Component: | HIV / AIDS | Grant No. | GHA-H-GAC-786 | Start Date: |  | 2015-07-01 | Total Funding | 12905454
Round: | Round 9 | Phase: | NFM | Principal Recipient: |  | Ghana AIDS Commission
Report Period: | Q1 | from: | 2015-07-01 | to: |  | 2015-09-30 | Latest Rating: | A1
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Mark Saalfeld
Prepared by: | GAC Core Team |  |  | Report preparation date: |  | 2015-11-15
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Ghana - HIV / AIDS
Round 9 | NFM |  |  |  | Report Period: |  | Q1
Latest Rating: | A1 |  | Ghana AIDS Commission |  | From: |  | 2015-07-01
|  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting |  |  |  | To: | 2015-09-30
Financial Indicators
F1: Budget and disbursements by Global Fund - in ($) Report Period: Q1 |  |  |  | F3: Disbursements and expenditures - in ($) Report Period: Q1
Comments: | The PR received $1,332,486 from the GF within the period |  |  | Comments: | $34667.45 was disbursement to SR within this period.
F2: Budget and actual expenditures by Grant Objective - in ($) Report Period: Q1 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: Q1
Comments: | The PR did not undertake any activities in HTC and Condom distribution |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 44
|  |  |  | Days taken for disbursement to reach PR |  | 10 | 10
|  |  |  | Days taken for disbursement to reach SRs |  | 3 | 3
Menu

## Management
Dashboard: Ghana - HIV / AIDS
Round 9 | NFM |  |  |  |  | Report Period: |  | Q1
Latest Rating: | A1 |  | Ghana AIDS Commission |  |  | From: |  | 2015-07-01
|  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting |  |  |  |  | To: | 2015-09-30
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: Q1 |  |  |  | M2: Status of key PR management positions Report Period: Q1
Comments: |  |  |  | Comments:
M3: Contractual arrangements (SRs) Report Period: Q1 |  |  |  | M4: Number of complete reports received on time Report Period: Q1
Comments: | The PR has only two SRs |  |  | Comments:
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: Q1
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Ghana - HIV / AIDS
Round 9 | NFM | [8 empty] | Report Period: |  | Q1
Latest Rating: | A1 |  | Ghana AIDS Commission | [7 empty] | From: | 2015-07-01
|  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting | [8 empty] | To: | 2015-09-30 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Pr1. # male & female condoms distributed to FSW. |  |  |  | Pr2. # male condoms distributed to MSMs. |  |  |  | Pr3. # of FSW who received testing and counseling for HIV and received their test results
Comment: P1 | Prolong SR engagement leading to late start of implementation |  |  | Comment: P2 | Due to the change in the SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication |  |  | Comment: P3 | Prolong SR engagement leading to late start of implementation
Indicators |  |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Pr1. # male & female condoms distributed to FSW. |  |  | 1500000 | 0 | 0% |  |  | Prolong SR engagement leading to late start of implementation |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Pr2. # male condoms distributed to MSMs. |  |  | 100000 | 0 | 0% |  |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Pr3. # of FSW who received testing and counseling for HIV and received their test results |  |  | 1500 | 0 | 0% |  |  | Prolong SR engagement leading to late start of implementation | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr4. # of MSM who received testing and counseling for HIV and received their test results |  |  | 375 | 0 | 0% |  |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr5. # of FSW reached with HIV prevention programs (interventions) |  |  | 1380 | 0 | 0% |  |  | Prolong SR engagement leading to late start of implementation | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr6. # of MSM reached with HIV prevention programs (interventions) |  |  | 575 | 0 | 0% |  |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Pr7. # of PLHIV registered in the National Health Insurance Scheme |  |  | 500 | 1134 | 226.8% |  |  | Eventhough health facilities were required to refund to the PR by June 30, some facilities had made prior commitment to register clients onto the NHIS accounting for the overachievement | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 0 | 0 | 0% | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Ghana - HIV / AIDS
Round 9 | NFM |  |  |  |  | Report Period: | Q1
Latest Rating: | A1 |  | Ghana AIDS Commission |  |  | From: | 2015-07-01
|  |  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting |  |  | To: | 2015-09-30
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | The PR received $1,332,486 from the GF within the period
F2 |  | The PR did not undertake any activities in HTC and Condom distribution
F3 |  | $34667.45 was disbursement to SR within this period.
F4
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1
M2 |  |  | #DIV/0! | #DIV/0!
M3 |  | The PR has only two SRs
M4
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | Prolong SR engagement leading to late start of implementation
P2 - trend |  | Due to the change in the SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication
P3 - trend |  | Prolong SR engagement leading to late start of implementation
P1 |  | Prolong SR engagement leading to late start of implementation
P2 |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication
P3 |  | Prolong SR engagement leading to late start of implementation
P4 |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication
P5 |  | Prolong SR engagement leading to late start of implementation
P6 |  | Due to the change in SR arrangement for the MSM module, the PR and SR were unable to verify the MSM data and therefore has not been reported. The data will be reported in the next reporting cycle after verfication
P7 |  | Eventhough health facilities were required to refund to the PR by June 30, some facilities had made prior commitment to register clients onto the NHIS accounting for the overachievement
P8 |  | #REF!
P9 |  | #REF!
P10
Menu

## Actions
Dashboard: Ghana - HIV / AIDS
| Round 9 | NFM |  |  |  | Report Period: |  | Q1
| Latest Rating: | A1 |  | Ghana AIDS Commission |  | From: |  | 2015-07-01
|  |  | Reinforcing the Scaling Up of HIV Services: Strengthening HIV Prevention and Effective Targeting |  |  |  | To: | 2015-09-30
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Ghana - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | Q1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | Q2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | Q3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 | NFM | Q4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | Q5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | Q6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | Q7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | Q8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | Q9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | Q10 |  | STI (Swiss Tropical Institute), | DDI | Belize
[6 empty] | UNOPS | EFV | Benin
[7 empty] | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe

## Sheet1 (hidden)
jan to june 2012 | 1098
july to dec 2012 | 556.62
jan to june 2013 | 640.03
july to dec 2013 | 57868.79
jan to june 2014 | 3.38
july to dec 2014 | 82659.65
142826.47