## Menu
Dashboard: Ghana - MALARIA
MALARIA | Grant No.: GHA-MOH-M
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Ghana - MALARIA
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, May 2015) | Measurement | Data Source
Pr1. Proportion of estimated malaria cases (presumed and confirmed) that received first line anti-malarial treatment at health facilities | Numerator: number of suspected malaria cases given ACTs as treatment according to national guidelines Denominator: Number of suspected malaria cases for all the health facilities, whilst the | This indicator seeks to measure the number of projected malaria cases that will receive ACTs correctly. This captures all malaria cases in all health acilities in the country(both public and private). Diagnosis of uncomplicated or severe malaria can be (1) laboratory-confirmed in countries that routinely perform laboratory testing for malaria or (2) presumptive, based on clinical symptoms (such as in most high-endemicity countries in sub-Saharan Africa, where all cases of acute fever without an obvious nonmalarial cause are considered malaria). | MOH (HMIS (DHIMS))
Pr2. % Proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment (IPTp) for malaria | Numerator: Number of pregnant women who received at least three doses of intermittent preventive treatment with a recommended antimalarial drug during antenatal care visits Denominator: Total number of pregnant women at first antenatal care visits (registrants) | This measures the number of pregnant women who took at least three doses of SP during ANC visit according to national policy. Denominator: antenatal registrants per year. | MOH (HMIS (DHIMS))
Pr3. Number of long-lasting insecticidal nets distributed to at-risk populations through mass campaigns | Number of mosquito nets distributed to population (including pupils, pregnant women and children under five years), through mass campaign with the mosquito nets being limited to long-lasting insecticidal nets | Number of mosquito nets distributed to population (including pupils, pregnant women and children under five years), through mass campaign with the mosquito nets being limited to long-lasting insecticidal nets | MOH (Mass campaign report)
Pr4. Proportion of population at risk potentially covered by long lasting insecticidal nets distributed | Numerator: Population covered by available LLINs through mass campaign Denominator: Total population of regions covered | This seeks to measure the coverage of LLINs distributed through mass campaign | MOH (Mass campaign report)
Pr5. Proportion of suspected malaria cases that receive a parasitological test at health facilities | Numerator: number of malaria cases confirmed by RDTs or microscopy (total tested). Denominator: number of suspected cases of malaria | This information is collected through the health facility routine data collection system and laboratory records. High coverage is a key factor for interpreting the commitment in confirming (testing) all suspected malaria cases before treatment is given. | MOH (HMIS (DHIMS))
Pr6. Proportion of targeted risk groups (pupils, pregnant women and children under five years) receiving long-lasting insecticidal-nets through routine distribution | Number of risk groups (pupils, pregnant women and children under five years) who received LLINs over expected number of risk groups to be given LLINs. The denominator for risk groups are as follows: pregnant women = number of registrants, Children under five=children due for measeles 2, pupils= All people in class 2 and 6. | This seeks to measure the coverage of LLINs distributed through the ANC, Epi and Primary School | MOH (HMIS (DHIMS))
Pr7. Number of children under five years which received first-line antimalrial treatment according to national policy(ACTs) at the community level | Number of uncomplicated malaria cases among under 5 year children treated with ACT by community based health workers (CBA) | This measure the number of uder five children treated in the communities through the iCCM intervention. iCCM will be limited to communities with out access to Health facilities. | MOH (HMIS (DHIMS))
Pr8. Proportion of confirmed malaria cases that received first-line antimalarial treatment according to national policy at health facilities | Number of malaria positive cases treated over number of cases tested positive for malaria | This measures treatment of positive malaria cases according to national policy | MOH (HMIS (DHIMS))
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Ghana |  | Title of the Grant:
| Grant No.: | GHA-MOH-M |  | Component: |  | MALARIA | Total Funding: | 118095102
| Principal Recipient: | MOH |  |  | Round: | Please Select | Phase: | Please Select
| Start Date (dd/Mmm/yy): | 2015-03-01 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | Please Select |  | Fund Portfolio Manager: |  | Mark Saafield
Information reporting period
| Report Period: | P4 | From: | Oct | To: | Dec | Date of entry of information: |  | 2016-02-12
| Prepared by: |  | Whajib and Joel
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | $
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 31941964
| Reporting period | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | % Cumulative |  |  | 35548722
| Budget (in $) | P1: 31941964; P2: 3606758; P3: 4470214; P4: 4057400 | 86.18% |  |  | 40018936
| Disbursements by GF (in $) | P1: 0; P2: 13715970; P3: 0; P4: 24269538.22 |  |  |  | 44076336
| Cumulative budget | 31941964 | 35548722 | 40018936 | 44076336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Cumulative disbursements | 0 | 13715970 | 13715970 | 37985508.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
|  | 0% | 0% | 0% | 86.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0
F2: Budget and actual expenditures by Grant Objective
| Grant Objective(Module) | P1: Cumulative Budget (in $); P2: Cumulative Expenditures (in $); P3: % of budget; P4: burn rate; P5: Budget in P4; P6: Expenditure in P4; P7: Burn rate
| Vector control | P1: 28431032; P2: 24311035.89; P3: 64.5%; P4: 85.51%; P5: 474201; P6: 2603444.89; P7: 549%
| Case management | P1: 9316156; P2: 3807018.35; P3: 21.14%; P4: 40.86%; P5: 2788528; P6: 232658.35; P7: 8.343%
| Specific prevention interventions (SPI) | P1: 1084664; P2: 909504.12; P3: 2.461%; P4: 83.85%; P5: 258755; P6: 473079.12; P7: 182.8%
| HSS - Health information systems and M&E | P1: 2873954; P2: 1621554.91; P3: 6.52%; P4: 56.42%; P5: 287137; P6: 820675.91; P7: 285.8%
| HSS - Financial management | P1: 167140; P2: 34109.55; P3: 0.3792%; P4: 20.41%; P5: 44283; P6: 746.55; P7: 1.686%
| Program management | P1: 2203390; P2: 863391.23; P3: 4.999%; P4: 39.18%; P5: 30540; P6: 323829.23; P7: 1060%
[6 empty] | 3883444 | 4454434.05
114.7%
| Total | P1: 44076336; P2: 31546614.05; P4: OK: Data match
71.57%
| F3: Disbursements and expenditures | P1: P3:; P2: 67% |  |  |  | 0
0
|  | P1: Prior to reporting period; P2: Current reporting period; P3: Total Spent and Disbursement (in $) |  |  | 0
| Disbursed by Global Fund | P1: 13715870; P2: 24269538.22; P3: 37985408.22; P4: This disbursement includes VPP
| PR expenditure and disbursement | P1: 3304236; P2: 28242378; P3: 31546614; P4: Expenditure also includes VPP
| Disbursed to SRs | P1: 0; P2: 975658.36; P3: 975658.36
| SR expenditures | P1: 0; P2: 874539.44; P3: 874539.44
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | P1: 45; P2: 45
| Days taken for disbursement to reach PR | P1: 45; P2: 67
| Days taken for disbursement to reach SRs | P1: 20; P2: n/a; P3: Disbursements just started in November
| Management Information: | P6: Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) | P2: 3; P3: 2; P4: 0; P5: 5
| Time Bound Actions (TBAs) | P2: 0; P3: 0; P4: 0; P5: 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | P1: 1; P2: 0; P3: 1; P4: Was 6 during Q3?
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | P1: 184; P2: 184; P3: 61; P4: 61; P5: 61
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | P1: 0; P2: 0; P3: 0
| SRs to PR | P1: 0; P2: 0; P3: 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Budget Approved* | P1: 19978302.5; P2: 2045439.64; P3: 2277969.84; P4: 2045439.64
| Obligations | P1: 0
| Expenditures | P1: 0; P2: 2878482.63; P3: 17987514; P4: 3403541.22
| Budget Approved cumulative* | 19978302.5 | 22023742.14 | 24301711.98 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62 | 26347151.62
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 2878482.63 | 20865996.63 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85 | 24269537.85
92.11%
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| Please Select | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
|  | P6: Jan-Mar2015; P7: Apr-June 2015; P8: July-Sep 2015; P9: Oct-Dec 2015; P10: Jan-Mar 2016; P11: Apr-Jun 2016; P12: July-Sep 2016 | Oct-Dec 2016 | Jan-Mar 2017 | Apr-June 2017 | July-Sept 2017 | Oct-Dec 2017
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TOP 3 | Pr1. Proportion of estimated malaria cases (presumed and confirmed) that received first line anti-malarial treatment at health facilities |  |  |  | No | Target | P1: 80%; P2: 80%; P3: 80%; P4: 80%
[6 empty] | Achieved | P1: 79.9%; P2: 59.5%; P3: 58%; P4: 57%
| Pr2. % Proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment (IPTp) for malaria |  |  |  | No | Target | P1: 55%; P2: 55%; P3: 55%; P4: 55%
[6 empty] | Achieved | P1: 39.2%; P2: 42%; P3: 51.25%; P4: 41%
| Pr3. Number of long-lasting insecticidal nets distributed to at-risk populations through mass campaigns |  |  |  | No | Target | P1: 2692264; P2: 2692264; P3: 5913034; P4: 5913034
[6 empty] | Achieved | P1: 0; P2: 2942234; P3: 252723; P4: 5129002
| Pr4. Proportion of population at risk potentially covered by long lasting insecticidal nets distributed |  |  |  | No | Target | P1: 92.8%; P2: 92.8%; P3: 96.5%; P4: 96.5%
[6 empty] | Achieved | P1: 0%; P2: 97.1%; P3: 0%; P4: 90%
| Pr5. Proportion of suspected malaria cases that receive a parasitological test at health facilities |  |  |  | Yes | Target | P1: 70%; P2: 70%; P3: 75%; P4: 75%
[6 empty] | Achieved | P1: 90.6%; P2: 70.96%; P3: 72.7%; P4: 74%
| Pr6. Proportion of targeted risk groups (pupils, pregnant women and children under five years) receiving long-lasting insecticidal-nets through routine distribution |  |  |  | No | Target | P1: 0%; P2: 0%; P3: 86.9%; P4: 87%
[6 empty] | Achieved | P1: 0%; P2: 0%; P3: 0%; P4: 79%
| Pr7. Number of children under five years which received first-line antimalrial treatment according to national policy(ACTs) at the community level |  |  |  | Yes | Target | P1: 52963; P2: 105926; P3: 185372; P4: 264817
[6 empty] | Achieved | P1: 28163; P2: 59457; P3: 101376; P4: 153057
| Pr8. Proportion of confirmed malaria cases that received first-line antimalarial treatment according to national policy at health facilities |  |  |  | Yes | Target | P1: 100%; P2: 100%; P3: 100%; P4: 100%
[6 empty] | Achieved | P1: 100%; P2: 100%; P3: 100%; P4: 100%
[5 empty] | Yes | Target
Achieved
[5 empty] | Yes | Target
Achieved
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
| Pr1. Proportion of estimated malaria cases (presumed and confirmed) that received first line anti-malarial treatment at health facilities |  |  |  | No | Target | 80% | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 79.9% | 0.595 | 0.58 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pr2. % Proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment (IPTp) for malaria |  |  |  | No | Target | 55% | 0.55 | 0.55 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 0.392 | 0.42 | 0.5125 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pr3. Number of long-lasting insecticidal nets distributed to at-risk populations through mass campaigns |  |  |  | No | Target | 2692264 | 2692264 | 5913034 | 5913034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Achieved | 0 | 2942234 | 252723 | 5129002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B72: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B73: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B79: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B94: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Menu

## Grant Detail
Dashboard: Ghana - MALARIA
Country: | Ghana |  | Title of the Grant: |  | 0
Component: | MALARIA | Grant No. | GHA-MOH-M | Start Date: |  | 2015-03-01 | Total Funding | 118095102
Round: |  | Phase: |  | Principal Recipient: |  | MOH
Report Period: | P4 | from: | Oct | to: |  | Dec | Latest Rating:
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Mark Saafield
Prepared by: | Whajib and Joel |  |  | Report preparation date: |  | 2016-02-12
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Ghana - MALARIA
[5 empty] | Report Period: |  | P4
Latest Rating: |  |  | MOH |  | From: |  | Oct
|  | 0 |  |  |  | To: | Dec
Financial Indicators
F1: Budget and disbursements by Global Fund - in ($) Report Period: P4 |  |  |  | F3: Disbursements and expenditures - in ($) Report Period: P4
Comments: | This does not include funds disbursed to PPM and Co-payment unit. |  |  | Comments: | Grant was signed late and disbursement was late
F2: Budget and actual expenditures by Grant Objective - in ($) Report Period: P4 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P4
Comments: |  |  |  | Comments:
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 45
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 67
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | n/a
Menu

## Management
Dashboard: Ghana - MALARIA
[6 empty] | Report Period: |  | P4
Latest Rating: |  |  | MOH |  |  | From: |  | Oct
|  | 0 |  |  |  |  | To: | Dec
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P4 |  |  |  | M2: Status of key PR management positions Report Period: P4
Comments: | 3 CPs met, 2 CPs in progress |  |  | Comments: | Process for recruiting 3 data manger stared after approval was received. Epidemiologist and Lab- focal person transfer almost completed. Case management focal person yet to be identified
M3: Contractual arrangements (SRs) Report Period: P4 |  |  |  | M4: Number of complete reports received on time Report Period: P4
Comments: | No SRs engaged yet. SR recruitment is currently ongoing |  |  | Comments: | No report expected since no SR have been engaged
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P4
Comments: |  |  |  | Comments:
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | Please Select | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Ghana - MALARIA
[8 empty] | Report Period: |  | P4
Latest Rating: |  | MOH | [6 empty] | From: | Oct
| 0 | [7 empty] | To: | Dec | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Pr1. Proportion of estimated malaria cases (presumed and confirmed) that received first line anti-malarial treatment at health facilities |  |  | Pr2. % Proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment (IPTp) for malaria |  |  |  | Pr3. Number of long-lasting insecticidal nets distributed to at-risk populations through mass campaigns
Comment: P1 |  |  | Comment: P2 |  |  |  | Comment: P3
Indicators |  | Target | Achieved | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Pr1. Proportion of estimated malaria cases (presumed and confirmed) that received first line anti-malarial treatment at health facilities |  | 80% | 57% | 140.4% |  |  | 5821271 (57% ) out of 10159473 suspected malaria cases were treated with ACTs during the year under review. The reduction in use of ACTs is due to the increase in parasitological diagnosis of suspected malaria cases, thus reduction in over use of ACTs. |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Pr2. % Proportion of pregnant women attending antenatal clinics who received three or more doses of intermittent preventive treatment (IPTp) for malaria |  | 55% | 41% | 74.55% |  |  | Out of 944184 ANC registrants, 651725 (69%) received IPTp1, 547917 (58%) IPTp2 and 390256 (41.4%) IPTp3. This is because there still exist some documentation and supply chain challenges especially at periphery. Communication of availability of SP and late request from facility maybe attributed to non attainment of targtet. This challnges are being resoved during periodic monitoring and supervison. Also activities of NGO engaged at later part of 2015 will improve on uptake and compliance to IPTp doses by pregnant women. |  |  |  |  | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Pr3. Number of long-lasting insecticidal nets distributed to at-risk populations through mass campaigns |  | 5913034 | 5129002 | 86.74% |  |  | 5129002 (87% of expected LLINs to be distributed) LLINs distributed during the semester under review. 1469450 LLINs distributed in Central Region, 2952258 in Ashanti region and 707294 in Upper East. Meanwhile, yet to conduct post distribution validation in Central and Ashanti regions as well as distribution in Upper East region. LLINs point distribution campaign span from 2nd - 29th November, 2015 in Central region, 16th November - 13th December 2015 in Ashanti region and 25th December 2015 - 31st January, 2016 in Upper East region .Our inability to achieve the target was because The LLINs available were not adequate for Northern region campaign (as initially targeted in the) hence the change to Upper East region( whihc is smaller and needed less LLINs) instead. |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr4. Proportion of population at risk potentially covered by long lasting insecticidal nets distributed |  | 96.5% | 90% | 93.26% |  |  | A total population of 14,357,578 was covered through mass campaign in year under review. Thus the total cummulative coverage is 4,868,783 (2014 VR+ER coverage depreciated by 8%) +14,357,578 (2015 BAR+WR+CR+ASH+UE)= 19,226,361 instead of expected 20525908. This is because Northern region with estimated population of 2515605 was replaced with Upper East region with estimated population of 1110955 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr5. Proportion of suspected malaria cases that receive a parasitological test at health facilities |  | 75% | 74% | 98.67% |  |  | 7,481,651 out of 10,159,473 suspected malaria cases were tested within the semester under review. This achievement is due to ongoing promotion of testing before treatment and adequate supply of RDTs in the country. |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Pr6. Proportion of targeted risk groups (pupils, pregnant women and children under five years) receiving long-lasting insecticidal-nets through routine distribution |  | 87% | 79% | 90.8% |  |  | A total of 695137 children underfive and pregnant women received LLINs through ANC and CWC. |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
Pr7. Number of children under five years which received first-line antimalrial treatment according to national policy(ACTs) at the community level |  | 264817 | 153057 | 57.8% |  |  | Some implementation challenges including inadequate supervision by health workers have affected non-attainment of target.there is plans to focus on supporting the community health workers through the CHPS which will still ensure improved and appropriate treatment of malaria at the community level |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
Pr8. Proportion of confirmed malaria cases that received first-line antimalarial treatment according to national policy at health facilities |  | 1 | 1 | 100% |  |  | 3,035,993 tested positive cases were reported at the end of the period under review. All of these cases were treated with ACTs. |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  | 0 | 0 | 100% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
0 |  | 0 | 0 | 100% | [7 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[12 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Ghana - MALARIA
[5 empty] | Report Period: | P4
Latest Rating: |  | MOH |  |  | From: | Oct
|  | 0 |  |  | To: | Dec
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial | Summary Comments |  |  | Recommendations
F1 | This does not include funds disbursed to PPM and Co-payment unit.
F2
F3 | Grant was signed late and disbursement was late
F4
Are procurement and hiring on schedule?
Management | Summary Comments |  |  | Recommendations
M1 | 3 CPs met, 2 CPs in progress
M2 | Process for recruiting 3 data manger stared after approval was received. Epidemiologist and Lab- focal person transfer almost completed. Case management focal person yet to be identified | #DIV/0! | #DIV/0!
M3 | No SRs engaged yet. SR recruitment is currently ongoing
M4 | No report expected since no SR have been engaged
M5
M6
Are technical targets being achieved?
Programmatic | Summary Comments |  |  | Recommendations
P1 - trend
P2 - trend
P3 - trend
P1 | 5821271 (57% ) out of 10159473 suspected malaria cases were treated with ACTs during the year under review. The reduction in use of ACTs is due to the increase in parasitological diagnosis of suspected malaria cases, thus reduction in over use of ACTs.
P2 | Out of 944184 ANC registrants, 651725 (69%) received IPTp1, 547917 (58%) IPTp2 and 390256 (41.4%) IPTp3. This is because there still exist some documentation and supply chain challenges especially at periphery. Communication of availability of SP and late request from facility maybe attributed to non attainment of targtet. This challnges are being resoved during periodic monitoring and supervison. Also activities of NGO engaged at later part of 2015 will improve on uptake and compliance to IPTp doses by pregnant women.
P3 | 5129002 (87% of expected LLINs to be distributed) LLINs distributed during the semester under review. 1469450 LLINs distributed in Central Region, 2952258 in Ashanti region and 707294 in Upper East. Meanwhile, yet to conduct post distribution validation in Central and Ashanti regions as well as distribution in Upper East region. LLINs point distribution campaign span from 2nd - 29th November, 2015 in Central region, 16th November - 13th December 2015 in Ashanti region and 25th December 2015 - 31st January, 2016 in Upper East region .Our inability to achieve the target was because The LLINs available were not adequate for Northern region campaign (as initially targeted in the) hence the change to Upper East region( whihc is smaller and needed less LLINs) instead.
P4 | A total population of 14,357,578 was covered through mass campaign in year under review. Thus the total cummulative coverage is 4,868,783 (2014 VR+ER coverage depreciated by 8%) +14,357,578 (2015 BAR+WR+CR+ASH+UE)= 19,226,361 instead of expected 20525908. This is because Northern region with estimated population of 2515605 was replaced with Upper East region with estimated population of 1110955
P5 | 7,481,651 out of 10,159,473 suspected malaria cases were tested within the semester under review. This achievement is due to ongoing promotion of testing before treatment and adequate supply of RDTs in the country.
P6 | A total of 695137 children underfive and pregnant women received LLINs through ANC and CWC.
P7 | Some implementation challenges including inadequate supervision by health workers have affected non-attainment of target.there is plans to focus on supporting the community health workers through the CHPS which will still ensure improved and appropriate treatment of malaria at the community level
P8 | 3,035,993 tested positive cases were reported at the end of the period under review. All of these cases were treated with ACTs.
P9
P10
Menu

## Actions
Dashboard: Ghana - MALARIA
[5 empty] | Report Period: |  | P4
| Latest Rating: |  | MOH |  | From: |  | Oct
|  | 0 |  |  |  | To: | Dec
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Ghana - MALARIA
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe